## Slide 1
Background
Started with 2016 dialog with Smithsonian – to support 50th anniversary display
They decided not to display religious artifact, referred us to Museum of the Bible (MOTB)
Prior Session Committee formed to explore idea of a Chalice & Seal loan – lead by Allen Brown
Interrupted by Covid – now considering loan in Jan 2023 (details further down)
Recently new Session committee formed
Diane Kane, Jamee Wilson, Mary Lawrence, Al Strahan – Allen Brown consulting
Rev Keith recently pinged by MOTB showing renewed interest
Pick up where previous effort left off
NO commitment or recommendation has yet been made – Ultimately a Session decision
Concept
Chalice featured prominently in exhibit ‘Scripture & Science: Our Universe, Ourselves and Our Place’
  Including Vatican Astro-Quadrant & meteorite, Galileo observational notes, Dorothy Vaughn bible
MOTB opened in 2017, 2 blocks south of DC mall, 400,000+ sq ft, 6 floors, impressive facility
MOTB houses thousands of artifact
  arranged 91 loans of 400+ items last year – much experience with transport and security
Full disclosure
MOTB claims to not proselytize, yet has Evangelical backing (Hobby Lobby Greene family, etc)
Also, some early scandals involving antiquity acquisition (by museum backers, not museum)
We are in discussion with Daved Anthony Schmidt, Head of Collections and Curation
  professional, PhD in history, Presbyterian background
Exploring option to loan Lunar Chalice & Church Seal to Museum of the Bible
NO Decision Today – Status Only

## Slide 2
Timeline
‘Soft’ opening to VIPs on Jan 19, 2023; open to public the following day
Need to have Chalice and Seal by Jan 10, 2023 for a 1 year loan
Desire an agreement by October time frame, if possible
Ideally, this would be a Formal Session vote in late September (or special session in Oct)
  need vote of all Session members, not just a minimal quorum
Agreement
We have a draft agreement for review, updated from pre-covid
Formalize loan dates, with option to briefly return Chalice for Lunar Communion at MOTB cost
Clearly defines ownership, provenance, to be WPC (Clerk of Session would sign)
MOTB willing to cover insurance of items while in their custody to an agreed appraisal value
  consulting with expertise on how to appraise
  intent really is to incentivize MOTB to protect and return items
Also defines security during all of MOTB possession including transport
  they offer secure ‘white glove’ service where they transport
  or courier option where we accompany
  all at their expense
In addition, there is a Facility Report, defining aspects of display
  we intend to review/consult with manner of display
  we’d like to emphasize our Churches openness (Christ’s Communion table – open to all)
  also acknowledge that in middle of grand endeavor involving 100,000s,
    Buzz took time to thank God, solemn act of Communion
    ‘to pause for a moment…and to give thanks in his or her own way’

## Slide 3
In Work, next steps
Working with lawyer to review Loan Agreement
Also reviewing details of display, spirit of, etc.
  will circle back with MOTB with follow-up questions in a couple weeks
Working to secure an appraisal, and to further solidify our ownership (provenance)
We can post drafts of agreement and facility report on Session page
Desire for Feedback
WPC has a strong emotional connection to these artifacts
  some, including Jamee and Mary, part of July 20, 1969 Communion – Eagle landed 4+ hrs later
We still have current members who were part of the Apollo generation
Would not suggest a congregation vote
  not practical and not all invested to the same degree, and again this is a Session decision
instead suggest informal discussion during Bible Study, Covenant meetings, etc
Also, perhaps a meeting at The Crossing (use meeting space) targeting Apollo generation
Thoughts ?