Finance Committee Meeting Minutes

June 20, 2019

Submitted for committee by DK Snowden

The committee met with Pastor Keith, Jimmy Spivey, Paul Harano, and Kevin Snowden attending.  The bulk of the meeting focused on review of spending and an update on the capital campaign spending.

September 8th is targeted as ‘burning the mortgage’ event day.  The intent is to roll this joyous activity into other church activities at the time.

Jimmy’s treasurer’s report details income and payments through the end of May.   Summarizing, we are only  $742.22 behind on the budget.   Giving is $14.1K behind budget plan but spending is also $13.4 under budget.   As long as spending is low, we can counter the gap in giving.   The committee will continue to monitor giving and spending.

For the capital campaign, the project execution sequence was modified based on the discussion at the May Session meeting.   The focus is to blend needed seal and repair activities with campus enhancement projects completed prior to the 50th anniversary worship event on July 21st.   The committee met with Trinity Construction, project execution manager to review projects and timing.   Thanks to Paul Harano for his outstanding work in role as church representative on these projects.

Summarizing current active projects / activities

- Fellowship Hall phase 1, roof replacement, has been completed.  The roofers found little damage to the roof decking – very good result.

- The replacement lights for the main sanctuary are on a truck with expected arrival at or after June 26th.   Trinity is ready to execute lighting upgrade as efficiently as possible as soon as practical. The cost of this project has been reduced from $90K to $60K through Ken’s and Paul’s diligence.

- Replacing the two double door entrances to the Fellowship Hall has been removed from Trinity’s scope and will be managed by Campus Management; replacement will be bronze metal double doors with panic bars and will be installed prior to the 50th celebration.

- Fellowship Hall Phase 2 will start soon.   This project focuses on restucco the outside of the tower with new flashing/sealing; remove old gutters, repair rotted soffit and facia boards, paint as necessary, & then install new gutters; clean and seal stucco banding at eaves; repair water damage to the front interior wall.  At this time, we will delay spending money to totally upgrade the windows in the Fellowship Hall as the schedule for the 50th cannot be met

- Trinity will power wash the cross on the main sanctuary and the exterior stucco surfaces of the Education building as soon as the crew can be scheduled

- Seal and dry repairs to the main sanctuary will be completed prior to 50th celebration.   The work includes new roof and full replacement and sealing of all roof seams; the exterior brick seams will be replaced with a two part elastomeric sealant from roof eave to foundation; all stained glass windows will be cleaned and improved sealing provided around the perimeters; repair water damage on walls and ceiling.

The contractor recommend that we modify the tower section of the Fellowship Hall to better seal the entire tower and minimize future water penetration by removing the tile adornment.   This recommendation includes removing unserviceable vent unit at the top of the tower (direct water intrusion), removing the exterior tile cross, replacing all stucco, and then sealing with elastomeric paint.  The tiles would not be replaced at a project savings of approximately $11.5K.   These changes provide best opportunity for the long-term integrity of the surfaces to prevent water intrusion.

This will change the exterior look of the tower.   An informal review of this change by ten church members on Sunday, 23rd, were supportive of removing this decorative detail in the spirit of minimizing future damage and low cost long term maintenance.   The committee endorsed this change and asks that Session also endorse this modification to the exterior appearance of the tower.

The capital campaign recognizes that our instructions were to work towards balancing two important points:   where practical, divide project responsibilities between contractors and congregants & balance spending between seal and dry and the appearance of the church grounds.   And to do this without taking out loans to complete the work.   Here’s a summary of the work to meet these objectives.

Work completed by congregation members, but not part of capital campaign

- Landscaping and planting bed upkeep

- Butterfly garden / bee station

- Water collection barrels

- Japanese Garden renovation

- Meeting room cabinet replacement

- Power washing walking and parking areas and restriping of parking slots

Capital campaign completed

- Fellowship Hall roof replacement

Capital campaign projects in progress

- Power washing of cross and exterior stucco vertical surfaces facing NASA 1

- Fellowship Hall door replacement, tower upgrades, and interior wall repairs

- Sanctuary lighting upgrade

- Sanctuary windows cleaning and sealing

- Sanctuary roof replacement / seal

- Sanctuary seam upgrade and seal

- Interior water damage repair – walls and ceiling

Capital campaign projects that are not active because of lack of funds

- Education wing lighting replacements

- Admin building roof upgrade

- Fellowship Hall narthex window replacement (may progress after current active projects are completed

- Upgrade stained glass windows on Bouton (facing NASA 1)

- Main sanctuary air conditioning upgrade / other AC unit projects

Exterior view of Fellowship Hall tower