
WPC  ORGANIZATION COMMITTEE REPORT FOR SUMMER PROGRAM FOR MCWHIRTER
The organizing committee met May 2 at 6:30 pm to make plans for the summer program for McWhirter.   Present were Anya       xxx, Deena Hogue, Helen Deleon, Cappi McNeill, Linda Smith-Gregory and Kaylin Dupree.   Responsibilities were divided:


Anya—activities





Cappi—mentors



Deena—planning the menus



Linda—on site coordinator


Kaylin—registration




Phyllis Koenig—on site activities
The following decisions were made:


1.The dates for the program will be July 29 through August 14.  The meetings will be held on Tuesdays and Thursdays from 8 am to 2 pm.


2.Targeted participants will be 30 students from McWhirter and 10 children from WPC.
Mrs. Gramm will contact teachers for recommendations and send a letter of invitation to those children.  Linda will contact WPC families.

3.  There will be an effort to enlist some of the parents to assist, possibly in the kitchen, to build a friendly relationship between the parents and WPC.
4.  Kaylin will work with Hillary to draft the invitation.

5.  All committee members will try to recruit  WPC members to lead activities, help with meals, and mentor students in reading.

6.  Cappi and Kaylin will sort the books by reading level to be given to the children and prepare book a display.

7.  Based on students’ reactions last year, the menus will be redesigned to include more of the kids’ favorites, e.g. hot dogs, tacos, pizza, etc.

Since that meeting the following actions have been taken:


The program will be called SUMMER SPOTLIGHT to emphasize the importance of each individual child.  Anya  designed a logo showing a boy and a girl highlighted by  a spotlight from the cross.  This logo will be used on all our communications with McWhirter.



The invitations have been delivered, and the rooms have  been reserved.
